## Risk Matrix
Impact
|  | High | Medium | Low
| High | Organizational Changes Affecting Project Timelines
Probability |  | Unrealistic project timeline and time constraints
| Medium | Lack of understanding of customer requirements | Resource limits and team composition
|  | Technical Complexity and Integration Issues | Insufficient coverage and testing depth
|  | Data security and privacy concerns | Dependence on external systems and data
Integration issues with the client analytics team
| Low | Lack of expertise in the field of insurance | Lack of communication and cooperation among team members | Uncertain organizational changes
Lack of proper documentation and knowledge transfer

## Risk managing
Risk managing
Risk | Risk Level | Risk managing
Organizational Changes Affecting Project Timelines | High | - Regular communicating with customert for up-to-date information on planned changes that may affect project timelines. - Flexible project planning. - Set strict deadlines for customer feedback. - Active customer participation in the development process.
Unrealistic project timeline and time constraints | High | - Careful planning and evaluation of resources to ensure project timelines. - Regular monitoring of project progress.
Lack of understanding of customer requirements | High | - Regular meetings with the customer to clarify requirements. - Demo to ensure clear understanding of client requirements and expectations. - Development of requirements documentation and keeping it up to date throughout the project.
Technical Complexity and Integration Issues | High | - Conduct thorough analysis of technical requirements and integration points to identify potential problems before they occur. - Develop test plans and strategies that address the technical complexity and integration of systems. - Conduct regular collaborative tests to identify and troubleshoot problems.
Data security and privacy concerns | High | - Development and implementation of a strict data security policy. - Implement encryption and data access control mechanisms. - Conducting security audits. - Regularly updating data security systems.
Integration issues with the client analytics team | High | - Conducting regular meetings with the client's analytics team to understand their requirements and expectations. - Developing an integration plan to get the teams working together. - Involve representatives from the customer's analytics team in the development and testing process.
Lack of expertise in the field of insurance | Medium | - Provide training for the team to increase their understanding and knowledge of the insurance industry. - Hire professionals with insurance industry experience to consult the project. - Conduct a knowledge audit of the team to identify gaps and provide needed knowledge sessions.
Resource limits and team composition | Medium | - Estimate resources in advance and allocate sufficient resources to the project. - Plan the distribution of tasks among team members based on their skills and capacity. - Update regularly on the need for additional resources.
Insufficient coverage and testing depth | Medium | - Development of a detailed test plan. - Create traceabillity matrix to make sure that all requerements covered with tests. - Using automated tests to improve the efficiency and accuracy of testing.
Dependence on external systems and data | Medium | - Analyzing the reliability and availability of external systems and data. - Creating a backup and recovery plan. - Developing alternative action plans in the event of unavailability of external systems or data
Lack of communication and cooperation among team members | Low | - Regular use of effective means of communication (video conferencing, chats). - Organizing regular meetings and discussions to ensure interaction between team members. - Involving the team in collective decision-making.
Lack of proper documentation and knowledge transfer | Low | - Regularly update documentation according to changes and the progress of the project. - Organize knowledge transfer sessions.
Uncertain organizational changes | Low | - Analysis of organizational changes and their possible impact on the project. - Regular communication with the customer and stakeholders to obtain up-to-date information about planned changes.